## Work Plan
Draft workplan for |  | Name of project
Calendar Month ->
No. | Activity description | Deadline | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Remarks/Needs approval of
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Example
Draft workplan for
Name of project
|  |  | 2013-01-01 | 2013-01-01 | 2013-01-01 | 2013-01-01 | 2013-02-01 | 2013-02-01 | 2013-02-01 | 2013-02-01
No. | Activity description | Completion Deadline | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Remarks/Needs approval of
1 | Drafting SR transition plan for Phase 2 | bar: Week 1
2 | Phase 1 Evaluation | 2013-02-28 | [8 empty] | Approval of TORs by SPO pending | bar: Week 1 to Week 4
3 | Clarification to GF re Phase 2 budget | bar: Week 1
4 | Prepare response to GFATM quesries re NACP/PR2 issues | bar: Week 1
5 | Development of SR Managemen Manual | [9 empty] | Inputs required from all sections | bar: Week 1 to Week 2
6 | Meeting with physicians re FDC (Lahore) | 2013-01-22 | [8 empty] | Dr. XYZ to provide materials | bar: Week 3
7 | Redistribution of PIDS targets to current sites | [9 empty] | Head office approval required | bar: Week 2
8 | Request SRs to present performance at NACP | bar: Week 3
9 | Finalize reporting module of CHBC MIS | 2013-01-31 | bar: Week 2 to Week 4
10 | Request GFATM re LFA assessments of PACPs | 2013-01-31 | [8 empty] | Approvals required | bar: Week 3
11 | Preparation of CHBC reports for Q7 PUDR | 2013-01-21 | bar: Week 4
12 | PUDR Preparation - programmatic component | 2013-02-16 | bar: Week 3
13 | Prepare inputs for SR Management Letters | bar: Week 2
14 | MIS Orientation at Sargodha | TBD | bar: Week 1
15 | MIS Orientation at DG Khan | TBD | bar: Week 1
16 | MIS Orientation at Sukkur, Larkana | TBD | bar: Week 2
17
18
19
20